## Gantt DAS
Carta Gantt - Proyecto DAS
Alumno: Guillermo Schroeder |  |  |  | Mar | Mar | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun
Fase | Inicio | Fin | Duración | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Fase 1: Análisis y Requerimientos | 30/03/2026 | 05/04/2026 | 7 | bar: Mar to Apr
Fase 2: Estilos y Patrones Arquitectónicos | 06/04/2026 | 12/04/2026 | 7 | bar: Apr to Apr
Fase 3: Modelo 4+1 y Vistas Arquitectónicas | 13/04/2026 | 26/04/2026 | 14 | bar: Apr to Apr
Fase 4: Requisitos de Calidad y Principios de Diseño | 27/04/2026 | 10/05/2026 | 14 | bar: Apr to May
Fase 5: Prototipo | 11/05/2026 | 24/05/2026 | 14 | bar: May to May
Fase 6: Evaluación Heurística de Nielsen | 25/05/2026 | 31/05/2026 | 7 | bar: May to May
Fase 7: Control de Versiones | 01/06/2026 | 10/06/2026 | 10 | bar: Jun to Jun
Fase 8: Conclusiones, Bibliografía y Anexos | 11/06/2026 | 18/06/2026 | 8 | bar: Jun to Jun
Fase 9: Revisión Final y Entrega | 19/06/2026 | 23/06/2026 | 5 | bar: Jun to Jun